## STIME
Area | FASE | Attività | Risorsa | G/U REV 2
0. SETUP & FRAMEWORK | configurazione ambiente cloud | Provisioning Workspace & Unity Catalog | Cloud DevOps Engineer Senior | 5
0. SETUP & FRAMEWORK | configurazione ambiente cloud | Configurazione Networking & Azure ADLS | Cloud DevOps Engineer Senior | 2
0. SETUP & FRAMEWORK | configurazione ambiente cloud | Setup Repository Git & Pipeline di Deployment | Cloud DevOps Engineer Senior | 8
0. SETUP & FRAMEWORK | configurazione ambiente cloud | Sviluppo Skeleton Notebook Ingestion (Bronze) | Cloud Solution Architect | 7
0. SETUP & FRAMEWORK | configurazione ambiente cloud | Sviluppo Skeleton Notebook Cleansing (Silver) | Cloud Solution Architect | 5
0. SETUP & FRAMEWORK | configurazione ambiente cloud | Setup Centralizzato Error Handling & Logging | Cloud Solution Architect | 3 | 30
1. MASTER DATA | Analisi Tecnica | Analisi di dettaglio | Data Engineer Senior | 2
1. MASTER DATA | initial load | Initial load delle anagrafiche nel blob storage | Data Engineer Senior | 5
1. MASTER DATA | Articoli | Ingestion (Bronze) + Cleansing (Silver) | Cloud Solution Developer Senior | 3
1. MASTER DATA | Articoli | Mapping Dimensionale (Gold) | Cloud Solution Developer Senior | 2
1. MASTER DATA | Siti / Magazzini | Ingestion (Bronze) + Cleansing (Silver) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Siti / Magazzini | Mapping Dimensionale (Gold) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Fornitori | Ingestion (Bronze) + Cleansing (Silver) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Fornitori | Mapping Dimensionale (Gold) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Vettori / Autisti | Ingestion (Bronze) + Cleansing (Silver) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Vettori / Autisti | Mapping Dimensionale (Gold) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Soci / Punti Vendita | Ingestion (Bronze) + Cleansing (Silver) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Soci / Punti Vendita | Mapping Dimensionale (Gold) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Personale / Operatori | Ingestion (Bronze) + Cleansing (Silver) | Cloud Solution Developer Senior | 2
1. MASTER DATA | Personale / Operatori | Mapping Dimensionale (Gold) | Cloud Solution Developer Senior | 1
1. MASTER DATA | Quadratura e Certifica | Orchestrazione e Quadratura Anagrafiche | Data Analyst Senior | 4 | 27
2. PREP. SPEDIZIONI | Analisi Tecnica | Analisi di dettaglio | Data Engineer Senior | 2
2. PREP. SPEDIZIONI | Testate / Righe Bolle | Ingestion (Source to Bronze) | Cloud Solution Developer Senior | 4
2. PREP. SPEDIZIONI | Testate / Righe Bolle | Cleansing & Deduplica (Bronze to Silver) | Cloud Solution Developer Senior | 8
2. PREP. SPEDIZIONI | Testate / Righe Bolle | Denormalizzazione & Join (Silver to Gold) | Cloud Solution Developer Senior | 12
2. PREP. SPEDIZIONI | Turni / Produttività | Logica Business Pause & Turni (Gold Fact) | Cloud Solution Developer Senior | 8
2. PREP. SPEDIZIONI | Aggregati Spedizioni | Preparazione Area DM (Gold Agg) | Cloud Solution Developer Senior | 4
2. PREP. SPEDIZIONI | Quadratura e Certifica | Fase di Parallelo & Quadratura Spedizioni | Data Analyst Senior | 12 | 50
3. GIACENZE & STOCK | Analisi Tecnica | Analisi di dettaglio | Data Engineer Senior | 2
3. GIACENZE & STOCK | Snapshot Giacenze | Ingestion (Bronze) | Cloud Solution Developer Senior | 3
3. GIACENZE & STOCK | Snapshot Giacenze | Cleansing (Silver) | Cloud Solution Developer Senior | 5
3. GIACENZE & STOCK | Snapshot Giacenze | Storicizzazione & Valorizzazione (Gold Fact) | Cloud Solution Developer Senior | 10
3. GIACENZE & STOCK | Mappa Fisica | Mapping Topografico Celle/Corsie (Gold Fact) | Cloud Solution Developer Senior | 4
3. GIACENZE & STOCK | Aggregate | Preparazione Aggregati Volumetrici (Gold Agg) | Cloud Solution Developer Senior | 3
3. GIACENZE & STOCK | Quadratura e Certifica | Fase di Parallelo & Quadratura Stock | Data Analyst Senior | 11 | 38
4. CARICHI (INBOUND) | Analisi Tecnica | Analisi di dettaglio | Data Engineer Senior | 2
4. CARICHI (INBOUND) | Bolle / Pesate | Ingestion (Bronze) | Cloud Solution Developer Senior | 4
4. CARICHI (INBOUND) | Bolle / Pesate | Cleansing (Silver) | Cloud Solution Developer Senior | 5
4. CARICHI (INBOUND) | Bolle / Pesate | Denormalizzazione & Join (Silver to Gold) | Cloud Solution Developer Senior | 10
4. CARICHI (INBOUND) | Performance Inbound | Preparazione Aggregati Lead Time (Gold Agg) | Cloud Solution Developer Senior | 5
4. CARICHI (INBOUND) | Quadratura e Certifica | Fase di Parallelo & Quadratura Ricevimenti | Data Analyst Senior | 9 | 35
5. TRASPORTI & ORDINI | Analisi Tecnica | Analisi di dettaglio | Data Engineer Senior | 2
5. TRASPORTI & ORDINI | Ordini / Viaggi | Ingestion (Bronze) | Cloud Solution Developer Senior | 4
5. TRASPORTI & ORDINI | Ordini / Viaggi | Cleansing (Silver) | Cloud Solution Developer Senior | 5
5. TRASPORTI & ORDINI | Ordini / Viaggi | Denormalizzazione & Join (Silver to Gold) | Cloud Solution Developer Senior | 9
5. TRASPORTI & ORDINI | Costi / Servizio | Ripartizione Noli & Fill Rate (Gold Agg) | Cloud Solution Developer Senior | 5
5. TRASPORTI & ORDINI | Quadratura e Certifica | Fase di Parallelo & Quadratura Trasporti | Data Analyst Senior | 10 | 35
PM | PM | PM | PM | 0
215